## Site Map QAHealth Rating
Parent Section | Subsection | Sub-subsection (If Applicable) | Points Received | Features in Sub-Subsection | Grade Per Subsection | Available Points | Parent Section Grade | On Portal
Dashboard | Services |  | 0 | 2 | 0 | 0 | 0% | #DIV/0!
| My Tasks |  | 0 | 2 | 0
| Recent Projects |  | 0 | 2 | 0
| Following |  | 0 | 2 | 0
| Onboarding |  | 0 | 3 | 0
Home | General |  | 3 | 3 | 100% | 5 | 100% | 0%
| Upon Login |  | 2 | 2 | 100%
Explore | Individuals |  | 0 | 6 | 0% | 84 | 27.38% | 0%
| Organizations | All Organizations | 4 | 9 | 44.44%
|  | Individual Profile Pages | 17 | 28 | 60.71%
|  | Edit Profile Page | 2 | 28 | 7.143%
| Discusions |  | 0 | 3 | 0%
| Events |  | 0 | 1 | 0%
| My Inventory |  | 0 | 8 | 0%
| All Projects |  | 0 | 1 | 0%
Learn | Terms |  | 0 | 6 | 0% | 6 | 0% | 0%
Assemble | Make Application |  | 0 | 3 | 0% | 55 | 47.27% | 0%
| Publish Application |  | 0 | 8 | 0%
| My Projects | My Projects | 11 | 19 | 57.89%
|  | Sevices | 7 | 8 | 87.5%
|  | Tasks | 3 | 5 | 60%
|  | Discussions | 5 | 6 | 83.33%
|  | Team | 3 | 6 | 50%
Marketplace | Browsing |  | 0 | 5 | 0% | 17 | 0% | 0%
| Compairing |  | 0 | 6 | 0%
| Service Cards |  | 0 | 4 | 0%
| Share Services |  | 0 | 2 | 0%
DMDII Portal | Member Directory | Member Directory | 11 | 13 | 84.62% | 86 | 91.86% | 0%
|  | DMDII Member Profile | 9 | 9 | 100%
|  | Edit DMDII Member | 12 | 12 | 100%
| DMDII Projects | DMDII Projects | 11 | 14 | 78.57%
|  | Project Profile page | 13 | 13 | 100%
|  | Edit DMDII Projects | 17 | 17 | 100%
|  | Project Content | 5 | 7 | 71.43%
| About DMDII Member | About DMDII Member | 1 | 1 | 100%
UserDrop-down | My Account |  | 8 | 9 | 88.89% | 43 | 74.42% | 0%
| My Profile |  | 15 | 19 | 78.95%
| Add DMDII Content |  | 2 | 7 | 28.57%
| My Projects |  | 1 | 1 | 100%
| Create DMDII Member |  | 1 | 1 | 100%
| Create DMDII Project |  | 3 | 3 | 100%
| Logout |  | 2 | 3 | 66.67%
Footer | Footer links |  | 4 | 5 | 80% | 5 | 80% | 0%
Overall Weighted Grade | [6 empty] | 55.13%
[7 empty] | 100% | <- Dummy Cells for data bars
[7 empty] | Dummy Cell for Portal Bars | 100%
[7 empty] | Dummy Cell for Subsection Grades | 100%

## Home
Sub Category | Feature Name | Actions to test feature | Working 1/0 | Portal? | Evaluation | Calculations | more background calculations
Not Logged In | Dashboard README | Click on VIEW | 1 | 0 | Can be added | 1 | 1
| Marketplace README | Click on VIEW | 1 | 0 | Can be added | 1 | 1
| Community README | Click on VIEW | 1 | 0 | Can be added | 1 | 1
Total |  |  | 3 |  |  |  | 3
Logged In | Modal Pop-up Existing Organization | Log in, and you should be a ble to click and choose an existing organization from the auto populate upon type menu | 1 | 0 | Can be added | 1 | 1
| Modal Pop-up New Organization | Log in, and you should be able to click on other, after accepting the terms and conditions you should be sent to a page to create a new organization. You should be able to save the new organization. | 1 | 0 | Can be added | 1 | 1
Total |  |  | 2 |  |  |  | 2
Uber Total |  |  | 5 | 0% | 0 | <-Items added to portal
Grade |  |  | 100% | above is percent of functional beta feature on Portal. Over 100% marks merged features that are not functional (Will be highlighted in red), 100% mean all functional beta feature are merged into Portal (Will be marked in Green), less than 100% means not all functional beta features are merged into Portal (Will be blue).

## Explore
Sub Category | Feature Name | Actions to test feature | Score 1/0 (enterdate) | Portal? | Evaluation | Calculations |  | more background calculations
Individuals | Search |  |  |  | DO NOT ADD | 0 |  | 1
| Show |  |  |  | DO NOT ADD | 0 |  | 1
| Sort |  |  |  | DO NOT ADD | 0 |  | 1
| Pagination |  |  |  | DO NOT ADD | 0 |  | 1
| Information Card |  |  |  | DO NOT ADD | 0 |  | 1
| User Card | Able to Click on name, able to rate, able to view company, able ot view description, and able to add to a projects |  |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 6
All Organizations | All organizations cards appear | Check to see if the number of cards listed at the top of the page show up as cards on page when filter show all is selected | 1 |  | Can be added | 1 |  | 1
| Visit organization profile pages | Attempt to visit a few company profile pages and make sure they match the card you clicked on | 1 |  | Can be added | 1 |  | 1
| All organization logos appear if they were uploaded | Go to the company page with logo on card and check to see if profile has the same logo. Go to a company without logo on card and check to see if they have a logo on profile page. | 0 |  | DO NOT ADD | 0 |  | 1
| Show filter | Use the show filter to see if it is showing that many organization cards on the page. | 1 |  | Can be added | 1 |  | 1
| Search Filter | Try searching for a company that shows up in the show 25 items list but not the show 10 items list. | 0 |  | DO NOT ADD | 0 |  | 1
| Sort Filter | Use the sort filter to see if it is working | 1 |  | Can be added | 1 |  | 1
| Browse By (Left hand side) | Use the browse by options to see if the number of items claining to be in list show up on page | 0 |  | DO NOT ADD | 0 |  | 1
| Clear Filter in Browse By | Clicking on clear filter removes the filter you just createdin the browse by feature above | 0 |  | DO NOT ADD | 0 |  | 1
| Can Click in information button and retrieve all information here |  |  |  | DO NOT ADD | 0 |  | 1
Total |  |  | 4 |  |  |  |  | 9
Individual Organization Profile Page | Organization Profile: View Logo | Make sure these fields are filled for at leat three organizations | 0 |  | DO NOT ADD | 0 |  | 1
| Organization Profile: View Company Description |  | 1 |  | Can be added | 1 |  | 1
| Organization Profile: View Division |  | 1 |  | Can be added | 1 |  | 1
| Organization Profile: View Industry |  | 1 |  | Can be added | 1 |  | 1
| Organization Profile: View Location |  | 1 |  | Can be added | 1 |  | 1
| Organization Profile: View NAICS Code |  | 0 |  | DO NOT ADD | 0 |  | 1
| Request to Join |  | 0 |  | DO NOT ADD | 0 | does not send notification to organization admins | 1
| Follow |  | 1 |  | Can be added | 1 |  | 1
| View Storefront Redirects to Organization Storefront page |  | 1 |  | Can be added | 1 |  | 1
| Organization Profile: View Overview | When page loads up, overiew should be the selected tab, sections below should be awards received, Images and Videos. Make sure the three features all work/can be use. | 0 |  | DO NOT ADD | 0 |  | 1
| Organization Profile: View Skills | Make sure these fields are filled for at leat three organizations | 1 |  | Can be added | 1 |  | 1
| Add skill not on list that does not alrady exist on list |  | 0 |  | DO NOT ADD | 0 |  | 1
| Organization Profile: View Projects (Past colaboration, collaboration interests, past dmdii projects, upcoming dmdii project interests, content should all appear. |  | 1 |  | Can be added | 1 |  | 1
| Organization Profile: View History |  | 0 |  | DO NOT ADD | 0 |  | 1
| Organization Profile: View Contact |  | 1 |  | Can be added | 1 |  | 1
| Organization Profile: View Membership |  | 1 |  | Can be added | 1 |  | 1
| Organization Profile: View Reviews Rating Average |  | 0 |  | DO NOT ADD | 0 |  | 1
| Organization Profile: Able to leave a review |  | 0 |  | DO NOT ADD | 0 |  | 1
| Organization Profile: Able to Sort reviews |  | 0 |  | DO NOT ADD | 0 |  | 1
| Verified Members appear | Make sure that when a verified member is created they appear in this location | 1 |  | Can be added | 1 |  | 1
| Orgnization Administrators only show up once | Ensure that verified organization administrator only appear in the list of verified admins once. | 1 |  | Can be added | 1 |  | 1
| Unverified members appear | Unverified members should appear here | 1 |  | Can be added | 1 |  | 1
| Change Member role | Members' roles can be changed ro admin, and member | 1 |  | Can be added | 1 |  | 1
| Become an organization member/admin | Superuser and organization admins are able to make organization admins and members | 1 |  | Can be added | 1 |  | 1
| Remove a verified member | As a superuser or organization admin, able to remove a verified account | 1 |  | Can be added | 1 |  | 1
| Edit Company | Organization Admin and Superuser only, can click on this button and redirects to a form to edit the organization page | 0 |  | DO NOT ADD | 0 | only works in google chrome | 1
| Edit DMDII Member Profile | Organization Admin and Superuser only, can click on this button and redirects to a form to edit the organization's dmdii member profile page | 1 |  | Can be added | 1 |  | 1
| Delete Company | Organization Admin and Superuser only, can click on this button to delete the company. | 0 |  | DO NOT ADD | 0 |  | 1
Total |  |  | 17 |  |  |  |  | 28
Edit My Organization Profile | Edit-Form Accessibility | Form is accessible to Superusers and organization admin only | 1 |  | Can be added | 1 |  | 1
| All fields are filled with previously entered data | Check to make sure previously filled information is prepoulated in all related fields | 1 |  | Can be added | 1 |  | 1
| Able to change organization name | Able to add and remove all of these items | 0 |  | DO NOT ADD | 0 |  | 1
| Able to change division |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to change Industry |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to change NAICS code |  | 0 |  | DO NOT ADD | 0 | when saved does not appear on the organization profile page | 1
| Able to remove logo |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to Upload new logo |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to update Description |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to add new awards |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to remove awards |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to upload images |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to remove images |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to upload Videos |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to remove Videos |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to add skill on list |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to add skill not on list |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to remove skill |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to add past collaborations |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to add collaboration interests |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to add past DMDII projects |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to add upcoming DMDII project interests |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to remove past DMDII projects |  | 0 |  | DO NOT ADD | 0 |  | 1
| Alble to remove upcoming DMDII project interests |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to add new contact information |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to remove old contact information |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to add resaon for joining DMDII |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to remove reason for joining DMDII |  | 0 |  | DO NOT ADD | 0 |  | 1
Total |  |  | 2 |  |  |  |  | 28
Discusions | All the following items appear | Discussions you create |  |  | DO NOT ADD | 0 |  | 1
|  | Discussions you follow |  |  | DO NOT ADD | 0 |  | 1
|  | Discussions that are popuar |  |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 3
Events | All of the following items apear | Event name, time range, location, description, drop-down arrow to see more |  |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 1
My Inventory | Company Section | Able to view and edit logo |  |  | DO NOT ADD | 0 |  | 1
|  | Able to view and edit description |  |  | DO NOT ADD | 0 |  | 1
|  | Able to view and not edit the organization name |  |  | DO NOT ADD | 0 |  | 1
|  | Able to view and edit Store Banner |  |  | DO NOT ADD | 0 |  | 1
| Featured Section | removing form featured |  |  | DO NOT ADD | 0 |  | 1
|  | add to featured |  |  | DO NOT ADD | 0 |  | 1
|  | show filteed |  |  | DO NOT ADD | 0 |  | 1
|  | search storefront |  |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 8
All Projects | Has same functionality as My Projects |  | 0 |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 1
Uber Total |  |  | 23 | 0% | 0 | <-Items added to portal
Grade |  |  | 27.38% | above is percent of functional beta feature on Portal. Over 100% marks merged features that are not functional (Will bee highlighted in red), 100% mean all functional beta feature are merged into Portal (Will be marked in Green), less than 100% means not all functional beta features are merged into Portal (Will be blue).

## DMDII Portal
Sub Category | Feature Name | Actions to test feature | Score 1/0 (enterdate) | Portal? | Evaluation | Calculations |  | more backgorund calculations
Member Directory | Recent News | Make sure items appear | 0 |  | DO NOT ADD | 0 |  | 1
| Upcoming Events | Click on name, should pop up calendar and see event details, ensure dates match on calendar. (Past events do not display.) | 0 |  | DO NOT ADD | 0 |  | 1
| Calendar Widget | make sure it appears and events are highlighted on calendar | 1 |  | Can be added | 1 |  | 1
| Member Map | make sure on hover new york has at leas GE global research show up | 1 |  | Can be added | 1 |  | 1
| Search (company name only) | search for rolls and rolls-royce should show up, then clear the search field and click search again, items should come back. | 1 |  | Can be added | 1 |  | 1
| Show Filter | Should be able to click on show filter drop-down and choose 96 items. You should now see more members apear on the screen | 1 |  | Can be added | 1 |  | 1
| Company Categorical Information Correct | Make sure that items exist in each column | 1 |  | Can be added | 1 |  | 1
| Company Profile Redirect | Click on an organization name and make sure that the link redirects to the correct member profile page | 1 |  | Can be added | 1 |  | 1
| Project and Member Association Correct | Check to make sure that projects listed next to an organization have the organization listed on the project profile page | 1 |  | Can be added | 1 |  | 1
| Company Logo In Member Directory | Make sure that logos that appear next to the organization are the logos that appear on the member profile page | 1 |  | Can be added | 1 |  | 1
| Next Button | Ensure that the next button actually does bring up the next 12 organizations | 1 |  | Can be added | 1 |  | 1
| Browse By (Left Hand Side) | clear search should work, and filter by tier 2 and academic | 1 |  | Can be added | 1 |  | 1
| Clear Filter in Browse By | Clicking on clear filter removes the filter you just createdin the browse by feature above | 1 |  | Can be added | 1 |  | 1
Total |  |  | 11 |  |  |  |  | 13
DMDII Member Profile | Company Description Apears | Do a regular quality check and make sure all fileds are filled | 1 |  | Can be added | 1 |  | 1
| Member Tier Appears |  | 1 |  | Can be added | 1 |  | 1
| Member Since Apears in Correct Format |  | 1 |  | Can be added | 1 |  | 1
| Contacts Show Up |  | 1 |  | Can be added | 1 |  | 1
| Project Involvement Is Correct |  | 1 |  | Can be added | 1 |  | 1
| Storefront Appliations |  | 1 |  | Can be added | 1 |  | 1
| Awards/Recognitions are Correct |  | 1 |  | Can be added | 1 |  | 1
| Core Capabilities |  | 1 |  | Can be added | 1 |  | 1
| Desires Areas for Collaboration |  | 1 |  | Can be added | 1 |  | 1
Total |  |  | 9 |  |  |  |  | 9
Edit DMDII Member | All data is filled with previous entries | Got to a company profile page and click edit in the right hand corner of the page. Check to see that the data that appeared on the profile before is beeing filled in the field on the form. | 1 |  | Can be added | 1 |  | 1
| Previous Logo Appears | Current logo should appear on the page form | 1 |  | Can be added | 1 |  | 1
| Core Capabilities and Seeking Collaboration Items appear | Current chosen Core Capabilities and Seeking Collaboration Items should appear on the page form. | 1 |  | Can be added | 1 |  | 1
| Can add new Capabilities and Collaboration items | Removed current data in all fields and replace with new data, then check to see if all changes have taken effect on the member profile page | 1 |  | Can be added | 1 |  | 1
| Can remove Capabilities and Collaboration items |  | 1 |  | Can be added | 1 |  | 1
| Can remove Contacts |  | 1 |  | Can be added | 1 | This was not working Friday | 1
| Can add addition contacts |  | 1 |  | Can be added | 1 |  | 1
| Can remove awards |  | 1 |  | Can be added | 1 | this was not working friday | 1
| can add new awards |  | 1 |  | Can be added | 1 | this was not working friday | 1
| Can change organization membership tier |  | 1 |  | Can be added | 1 |  | 1
| Can change Member since and till dates |  | 1 |  | Can be added | 1 |  | 1
| Can update company description |  | 1 |  | Can be added | 1 |  | 1
Total |  |  | 12 |  |  |  |  | 12
DMDII Projects | Recent News | Check to see if News title 3 -1 appear on the page (most recent date news should be at the top of the list). | 0 |  | DO NOT ADD | 0 |  | 1
| Events time line | Make sure event 1 -3 appear on the time line in order. Hovering over markers should also bring up a popup | 0 |  | DO NOT ADD | 0 |  | 1
| most recent project overview appears | make sure if an overview was uploaded that it is currently appearing | 1 |  | Can be added | 1 |  | 1
| most recent project status appears | make sure if project status was uploaded that it is currently appearing on the page | 1 |  | Can be added | 1 |  | 1
| All types of quick links work | One of each type of quick link should work in the quick links section. One should provide text information, two should provide a link to a web page, and three should be a document. | 0 |  | DO NOT ADD | 0 | document quick links do not take you to the document that was uploaded. Modal acts as a test quicklink | 1
| search | Search for the third project on the list to make sure it appears. Use just one word from the project name. | 1 |  | Can be added | 1 |  | 1
| show filter | Click on show filter drop down and choose 96 items. All projects should now be visible that were appear on all following pages | 1 |  | Can be added | 1 |  | 1
| Projects appear in order according to project number | Check to make sure that projects are appearing in the order according to project number (by date: yyyy-call/projectNumber) | 1 |  | Can be added | 1 |  | 1
| Correct categorical information appears for projects | All columns should be filled with information. Click on a project name and check to see if what is listed in column matches what is listed on the project profile page | 1 |  | Can be added | 1 |  | 1
| project name link redirects to correct project profile | Check to see if project name links redirect to the correct project profile page | 1 |  | Can be added | 1 |  | 1
| able to visting member profile page by clicking on member name under project name | Find a project and click on the organizations listed under it's name. You should be redirected to the correct member profiles. Return to the project profile page and click on the links to the member profile pages. You should be redirected to the correct pages. | 1 |  | Can be added | 1 |  | 1
| Browse by (left hand side) | Click on awarded, product lifecycle management, and intelligent machining, scheck to see if projects show up that should, if non should then check to see that non did. | 1 |  | Can be added | 1 |  | 1
| Clear Filter in Browse By | Clicking on clear filter removes the filter you just createdin the browse by feature above | 1 |  | Can be added | 1 |  | 1
| Click the Next button | Change the show filter to 12. Refresh the page, then clicking on the next button should take you to the next page of projects. | 1 |  | Can be added | 1 |  | 1
Total |  |  | 11 |  |  |  |  | 14
Project Profile page | Project Status Correct | All of these sections should be filled in with the correct formating | 1 |  | Can be added | 1 |  | 1
| Project Name Correct |  | 1 |  | Can be added | 1 |  | 1
| Project number correct (format correct) |  | 1 |  | Can be added | 1 |  | 1
| Thrust Area Correct |  | 1 |  | Can be added | 1 |  | 1
| Project Financial Correct (format correct) |  | 1 |  | Can be added | 1 |  | 1
| Project Award and Estimated completion date correct |  | 1 |  | Can be added | 1 |  | 1
| Contributer correct (as well as catagorical type correct) |  | 1 |  | Can be added | 1 |  | 1
| Project summary up to date |  | 1 |  | Can be added | 1 |  | 1
| Project schedule appears |  | 1 |  | Can be added | 1 |  | 1
| all project updates appear and are in the correct order |  | 1 |  | Can be added | 1 |  | 1
| uploaded projects documents appear | Uploaded items should appear and you should be able to click on them to view the images | 1 |  | Can be added | 1 |  | 1
| project doucument are viewable |  | 1 |  | Can be added | 1 |  | 1
| who can view information is working |  | 1 |  | Can be added | 1 |  | 1
Total |  |  | 13 |  |  |  |  | 13
Edit DMDII Projects | All fields are filled with correct, and previously filling information | Check to make sure that all fields are automatically filled with data that was entered prviously | 1 |  | Can be added | 1 | date information is missing in firefox browsers | 1
| Title can be changed | All of these items fields need to be changed and checked to see if it is possible to update everything | 1 |  | Can be added | 1 |  | 1
| project award date and complete date can be changed |  | 1 |  | Can be added | 1 |  | 1
| project status can be updated |  | 1 |  | Can be added | 1 |  | 1
| project number can be updated |  | 1 |  | Can be added | 1 |  | 1
| cost share can be updated |  | 1 |  | Can be added | 1 |  | 1
| DMDII funding can be updated |  | 1 |  | Can be added | 1 |  | 1
| Focus area can be updated |  | 1 |  | Can be added | 1 |  | 1
| thrust area can be updated |  | 1 |  | Can be added | 1 |  | 1
| prime organization can be changed |  | 1 |  | Can be added | 1 |  | 1
| contributing organizations can be removed |  | 1 |  | Can be added | 1 |  | 1
| contributing organizations can be added |  | 1 |  | Can be added | 1 |  | 1
| Principle Investigator can be removed |  | 1 |  | Can be added | 1 |  | 1
| Principle Investigator can be added |  | 1 |  | Can be added | 1 |  | 1
| Point of Contact can be removed |  | 1 |  | Can be added | 1 |  | 1
| point of contact can be added |  | 1 |  | Can be added | 1 |  | 1
| Above can all be done for preawarded and awarded projects | Edit both preawarded and awarded projects and see if changes can take place. | 1 |  | Can be added | 1 |  | 1
Total |  |  | 17 |  |  |  |  | 17
Project Content | Project updates can be created | Create 5 project updates in the following order: Update 4 May 4 2015, Update 1 Jan 1 2010, Update 5 October 5 2014, Update 3 April 3 2012, and Update 2 February 2 2011. | 1 |  | Can be added | 1 |  | 1
| Project updates content and order | Updates appear in the right order and have the correct content | 0 |  | DO NOT ADD | 0 |  | 1
| Project Documents can be uploaded | Upload a .png image file. The file must have a no space in the name and remove any special characters and this may cause other problems. Than check if the file was uploaded and shows up in on the project profile. | 1 |  | Can be added | 1 |  | 1
| Project Financials can be uploaded |  | 1 |  | Can be added | 1 |  | 1
| Project Schedule can be uploaded |  | 1 |  | Can be added | 1 |  | 1
| Project Documents can be deleted | As a superuser click on delete next to the project document to delete it | 1 |  | Can be added | 1 |  | 1
| Project updaes can be deleted | As a superuser click on delete next to the project update to delte it | 0 |  | DO NOT ADD | 0 |  | 1
Total |  |  | 5 |  |  |  |  | 7
About DMDII Member | Item in Member Portal Drop-down appears for non-verified members. | Log in a a non-DMDII Member account. Click on the member drop-down menu. You should see on an option of About DMDII Members. | 1 |  | Can be added | 1 |  | 1
Total |  |  | 1 |  |  |  |  | 1
Uber Total |  |  | 79 | 0% | 0 | <-Items added to portal
Grade |  |  | 91.86% | above is percent of functional beta feature on Portal. Over 100% marks merged features that are not functional (Will bee highlighted in red), 100% mean all functional beta feature are merged into Portal (Will be marked in Green), less than 100% means not all functional beta features are merged into Portal (Will be blue).

## UserDrop-down
Sub Category | Feature Name | Actions to test feature | Score 1/0 (enterdate) | Portal? | Evaluation | Calculations | Comments | more background calculations
My Account | Account Basics: Update Information | Able to update items such as display name, location, e-mail address, First and Last names. | 1 |  | Can be added | 1 |  | 1
| Account Basics: Organization Verification | Able to use verification token to become associated with organization as regular member and organization admin | 1 |  | Can be added | 1 |  | 1
| Create new organization | Create New Organization button redirects to the correct form, and you are able to save that form to create new organization. Must be able to vist new organization profile pages. | 1 |  | Can be added | 1 |  | 1
| Privacy | Able to add public informaion, member information and Private information to account and save. | 1 |  | Can be added | 1 |  | 1
| Notification | Able to set notification settings | 0 |  | DO NOT ADD | 0 |  | 1
| Servers | Able to add default and own servers to your account. Shuld be able ot add server to a service in a project. | 1 |  | Can be added | 1 |  | 1
|  | Able edit and save server information for an existing server | 1 |  | Can be added | 1 |  | 1
|  | Able to delete an existing server. | 1 |  | Can be added | 1 |  | 1
|  | Able to create public server and can be accessed by others | 1 |  | Can be added | 1 |  | 1
Total |  |  | 8 |  |  |  |  | 9
My Profile | Edit Profile and Save | Previously entered information comes up | 1 |  | Can be added | 1 |  | 1
|  | Able to upload images | 1 |  | Can be added | 1 |  | 1
|  | Able add location | 1 |  | Can be added | 1 |  | 1
|  | Able to remove location | 1 |  | Can be added | 1 |  | 1
|  | Able to add a description | 1 |  | Can be added | 1 |  | 1
|  | Able ot remove description | 1 |  | Can be added | 1 |  | 1
|  | Able to add job title | 1 |  | Can be added | 1 |  | 1
|  | Able to remove job title | 1 |  | Can be added | 1 |  | 1
|  | Able to add skills | 1 |  | Can be added | 1 |  | 1
|  | Able to remove skills | 0 |  | DO NOT ADD | 0 |  | 1
| On profile the following shows up: Title, description, skills, location, company name | Check the user profile page to make sure these items all show up. | 1 |  | Can be added | 1 |  | 1
| See Own Skills | Able to view these items | 1 |  | Can be added | 1 |  | 1
| See History |  | 0 |  | DO NOT ADD | 0 |  | 1
| View All History |  | 0 |  | DO NOT ADD | 0 |  | 1
| View All Mutual |  | 0 |  | DO NOT ADD | 0 |  | 1
| View Review Rating |  | 1 |  | Can be added | 1 |  | 1
| View All Reviews |  | 1 |  | Can be added | 1 |  | 1
| Leave a review about yourself | Able to rate yourself | 1 |  | Can be added | 1 |  | 1
| Sorting | Able to use the sort feature to read reviews | 1 |  | Can be added | 1 |  | 1
Total |  |  | 15 |  |  |  |  | 19
Superuser: Add DMDII Content | Quick Links | Add one of each of the link type: text, url, document (image file) | 0 |  | DO NOT ADD | 0 |  | 1
| Member Events | Add a member event and make sure it shows up in the member directory page | 0 |  | DO NOT ADD | 0 |  | 1
| Member News | Add member news and make sure it shows up in the member directory page | 0 |  | DO NOT ADD | 0 |  | 1
| Project Events | Add a project event and make sure it shows up in the DMDII projects page | 0 |  | DO NOT ADD | 0 |  | 1
| Project News | Add project news and make sure it shows up in the DMDII projects page | 0 |  | DO NOT ADD | 0 |  | 1
| Projects Overview | upload and image make sure it shows up on the DMDII project page | 1 |  | Can be added | 1 |  | 1
| Projects Status |  | 1 |  | Can be added | 1 |  | 1
Total |  |  | 2 |  |  |  |  | 7
My Projects | Able to visit my projects section | In the user drop-down, select 'My Projects.' You should be redirected to the my projects section and see any projects you may have already created. | 1 |  | Can be added | 1 |  | 1
Total |  |  | 1 |  |  |  |  | 1
Superuser: Create DMDII Member | Upgrade Regular Organization to DMDII Member | Create a new organization and change it into the DMDII member. Check to make sure the member appears in the member directory | 1 |  | Can be added | 1 |  | 1
Total |  |  | 1 |  |  |  |  | 1
Superuser: Create DMDII Project | Create a DMDII awarded project | Create a new DMDII Project. Fill in all fields and check if information is maintained when you visit the project profile page | 1 |  | Can be added | 1 |  | 1
| Create a DMDII completed project |  | 1 |  | Can be added | 1 |  | 1
| Create a DMDII preawarded project |  | 1 |  | Can be added | 1 |  | 1
Total |  |  | 3 |  |  |  |  | 3
Logout | Log out of account | Log out of Account | 1 |  | Can be added | 1 |  | 1
| Data on screen does not persist | When logging out, you should no longer see anything you were working while you were logged in | 1 |  | Can be added | 1 |  | 1
| Can log in as other user in the same browsing session | Can click log in and not be automatically signed in as the same user whichout provide account credentials |  |  | DO NOT ADD | 0 |  | 1
Total |  |  | 2 |  |  |  |  | 3
Uber Total |  |  | 32 | 0% | 0 | <-Items added to portal
Grade |  |  | 74.42% | above is percent of functional beta feature on Portal. Over 100% marks merged features that are not functional (Will bee highlighted in red), 100% mean all functional beta feature are merged into Portal (Will be marked in Green), less than 100% means not all functional beta features are merged into Portal (Will be blue).

## Footer
Sub Category | Feature Name | Actions to test feature | Score 1/0 (enterdate) | Portal? (1/0) | Evaluation | Calculations | more background calculations
FAQs | Is the redirect working when logged in | Go to the following pages and make sure they redirect to the correct page | 1 |  | Can be added | 1 | 1
Terms of Service | Is the redirect working when logged in |  | 0 |  | DO NOT ADD | 0 | 1
Contacts Us | Is the redirect working when logged in |  | 1 |  | Can be added | 1 | 1
Feedback | Is the redirect working when logged in |  | 1 |  | Can be added | 1 | 1
Become a DMDII Member | Is the redirect working when logged in |  | 1 |  | Can be added | 1 | 1
Uber Total |  |  | 4 | 0% | 0 | <-Items added to portal | 5
Grade |  |  | 80% | above is percent of functional beta feature on Portal. Over 100% marks merged features that are not functional (Will bee highlighted in red), 100% mean all functional beta feature are merged into Portal (Will be marked in Green), less than 100% means not all functional beta features are merged into Portal (Will be blue).

## Assemble
Sub Category | Feature Name | Actions to test feature | Score 1/0 (enterdate) | Portal? (1/0) | Evaluation | Calculations |  | more backgound calculations
Make Application | Application Upload | Able to fill out the fields as such, cost with free option along with any of the others, when choosing free, any numbers already in the dollar amount field should be removed this field should no long ber updateable. Should also be able to add your own license and be able to choose standard license, when doing so the actual license field should erase anything that was there beforehand. This can be done over a to consecutive uploads. |  |  | DO NOT ADD | 0 |  | 1
| Static Content |  |  |  | DO NOT ADD | 0 |  | 1
| Publish Application |  |  |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 3
Publish Application | Fill Out Part One of form | Change Name |  |  | DO NOT ADD | 0 |  | 1
|  | Change Service Type |  |  | DO NOT ADD | 0 |  | 1
|  | Change Service Description |  |  | DO NOT ADD | 0 |  | 1
|  | Tagging |  |  | DO NOT ADD | 0 |  | 1
|  | Ensure # of inputs & outputs |  |  | DO NOT ADD | 0 |  | 1
| Fill Out Part Two of form | Author with User Card |  |  | DO NOT ADD | 0 |  | 1
|  | Documents |  |  | DO NOT ADD | 0 |  | 1
| Publish Application | Finish the process and chaeck that you are able to see the published service |  |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 8
My Projects | See All Your Created Projects | When more than one project is created, able to see all said projects in the "My Projects" section of the site. | 1 |  | Can be added | 1 |  | 1
| Sort Most Recent Projects | Be able to sort projects by the created date and alphabeticaly. | 1 |  | Can be added | 1 |  | 1
| Create a public project | Able to create both public projects where admin needs to provide approval and public projects where anyone can join. | 0 |  | DO NOT ADD | 0 |  | 1
| Create a private project | Able to create a private project | 1 |  | Can be added | 1 |  | 1
| Invite to public project | Able to invite people to a public project during the project creation process | 0 |  | DO NOT ADD | 0 |  | 1
| Invite to private project | Able to invite people to a private project during the project creation process | 1 |  | Can be added | 1 |  | 1
| Add a service to your public project | Able to add services to public projects | 0 |  | DO NOT ADD | 0 |  | 1
| Add a service to your private project | Able to add services to private projects | 1 |  | Can be added | 1 |  | 1
| Run a service in your public project | Users are able to run services that have been added to a public projects | 0 |  | DO NOT ADD | 0 |  | 1
| Run a service in your private project | Users are able to run services that have been added to a private projects | 1 |  | Can be added | 1 |  | 1
| Get results back from running service in public project | Results are returned to the screen when running a public project. | 0 |  | DO NOT ADD | 0 |  | 1
| Get results back from running serivice in private project | Results are returned to the screen when running a private project. | 1 |  | Can be added | 1 |  | 1
| Invitees can read results from service run in public project | After a service has been run, it is possible to view the results from the service runs. All users part of this project are able to view this. | 0 |  | DO NOT ADD | 0 |  | 1
| Invitees can read results from service run in private project |  | 1 |  | Can be added | 1 |  | 1
| View both Projects | Able to visit each of the project home pages that have been created when more than one project has been created. | 1 |  | Can be added | 1 |  | 1
| Can add tags to project | Can add tags to a project during project creation | 1 |  | Can be added | 1 |  | 1
| Can edit project | Able to edit a project, especially when other users are added to project | 0 |  | DO NOT ADD | 0 | when doing, others added to project are kicked out and are not reinvite-able | 1
| Can visit multiple projects | Able to visit project pages when more than one exists | 1 |  | Can be added | 1 |  | 1
| can add document to projects | Can add documents to projects during project creation and after the project has already been created. | 0 |  | DO NOT ADD | 0 |  | 1
|  |  | 11 |  |  |  |  | 19
Services | Services: Register service |  | 1 |  | Can be added | 1 |  | 1
| Service: service document upload |  | 1 |  | Can be added | 1 |  | 1
| Services: Able to add tags |  | 1 |  | Can be added | 1 |  | 1
| Services: edit a service |  | 1 |  | Can be added | 1 |  | 1
| Services: Remove a service |  | 1 |  | Can be added | 1 |  | 1
| Services: publish a service |  | 1 |  | Can be added | 1 |  | 1
| Services: running services |  | 1 |  | Can be added | 1 |  | 1
| Services: run service added to project from marketplace |  | 0 |  | DO NOT ADD | 0 |  | 1
|  |  | 7 |  |  |  |  | 8
My Projects: Tasks | create project tasks |  | 1 |  | Can be added | 1 |  | 1
| task created by has user name |  | 0 |  | DO NOT ADD | 0 |  | 1
| task assigned to has user name |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to open and close tasks |  | 1 |  | Can be added | 1 |  | 1
| edit task |  | 1 |  | Can be added | 1 |  | 1
|  |  | 3 |  |  |  |  | 5
My Projects: Discussions | Able to create discusion |  | 1 |  | Can be added | 1 |  | 1
| Able to tag discusion |  | 1 |  | Can be added | 1 |  | 1
| user picture is profile picture |  | 0 |  | DO NOT ADD | 0 |  | 1
| Able to comment is discusions |  | 1 |  | Can be added | 1 |  | 1
| able to like, dislike comments |  | 1 |  | Can be added | 1 |  | 1
| able to follow |  | 1 |  | Can be added | 1 |  | 1
|  |  | 5 |  |  |  |  | 6
team | See people on team |  | 1 |  | Can be added | 1 |  | 1
| remove people from project |  | 1 |  | Can be added | 1 |  | 1
| see pending approvals |  | 0 |  | DO NOT ADD | 0 |  | 1
| see active individuals |  | 1 |  | Can be added | 1 |  | 1
| See removed individuals |  | 0 |  | DO NOT ADD | 0 |  | 1
| invite new members to project |  | 0 |  | DO NOT ADD | 0 |  | 1
Total |  |  | 3 |  |  |  |  | 6
Uber Total |  |  | 26 | 0% | 0 | <-Items added to portal
Grade |  |  | 47.27% | above is percent of functional beta feature on Portal. Over 100% marks merged features that are not functional (Will bee highlighted in red), 100% mean all functional beta feature are merged into Portal (Will be marked in Green), less than 100% means not all functional beta features are merged into Portal (Will be blue).

## Learn
Sub Category | Feature Name | Actions to test feature | Working 1/0 | Portal? | Evaluation | Calculations | more background calculations
Learn Subsections Pages | Terms | All of the these static pages do load |  |  | DO NOT ADD | 0 | 1
| About DMC |  |  |  | DO NOT ADD | 0 | 1
| Contribute |  |  |  | DO NOT ADD | 0 | 1
| Shopfloor |  |  |  | DO NOT ADD | 0 | 1
| Workforce |  |  |  | DO NOT ADD | 0 | 1
| How To Guides |  |  |  | DO NOT ADD | 0 | 1
Total |  |  | 0 |  |  |  | 6
Uber Total |  |  | 0 | #DIV/0! | 0 | <-Items added to portal
Grade |  |  | 0% | above is percent of functional beta feature on Portal. Over 100% marks merged features that are not functional (Will be highlighted in red), 100% mean all functional beta feature are merged into Portal (Will be marked in Green), less than 100% means not all functional beta features are merged into Portal (Will be blue).

## Marketplace
Sub Category | Feature Name | Actions to test feature | Working 1/0 | Portal? | Evaluation | Calculations | Notes | more background calculations
Browsing | Browse By Filter | Analytical services, Solid Services, Data Services |  |  | DO NOT ADD | 0 |  | 1
| Show Filter | Able to filter by 12, 24, 48, 96 | 0 |  | DO NOT ADD | 0 |  | 1
| Filter by | Able to filter by author, rating, favorites, and date | 0 |  | DO NOT ADD | 0 |  | 1
| Search | Able to search for a service | 0 |  | DO NOT ADD | 0 |  | 1
| Sort | Able to sort by most popular services | 0 |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 5
Comparing | Able to compare up to 3 services |  | 0 |  | DO NOT ADD | 0 |  | 1
| Populated Fields |  | 0 |  | DO NOT ADD | 0 |  | 1
| Remove from compare |  | 0 |  | DO NOT ADD | 0 |  | 1
| Favorite it |  | 0 |  | DO NOT ADD | 0 |  | 1
| Remove all |  | 0 |  | DO NOT ADD | 0 |  | 1
| Add to project |  | 0 |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 6
Service Cards | View Specifications |  | 0 |  | DO NOT ADD | 0 |  | 1
| View Statistics |  | 0 |  | DO NOT ADD | 0 |  | 1
| View Tags |  | 0 |  | DO NOT ADD | 0 |  | 1
| View Doucments |  | 0 |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  |  |  | 4
Share Servies | Select from Memebes |  | 0 |  | DO NOT ADD | 0 |  | 1
| Favorite Services |  | 0 |  | DO NOT ADD | 0 |  | 1
Total |  |  | 0 |  |  | 0 |  | 2
Uber Total |  |  | 0 | #DIV/0! | 0 | <-Items added to portal
Grade |  |  | 0% | above is percent of functional beta feature on Portal. Over 100% marks merged features that are not functional (Will bee highlighted in red), 100% mean all functional beta feature are merged into Portal (Will be marked in Green), less than 100% means not all functional beta features are merged into Portal (Will be blue).

## Dashboard
Sub Category | Feature Name | Actions to test feature | Working 1/0 | Portal? | Evaluation | Calculations | more background calculations
Services | Able to view services in box |  |  |  | DO NOT ADD | 0 | 1
| Able to click on view all and be redirected to appropriate page |  |  |  | DO NOT ADD | 0 | 1
Total |  |  | 0 |  |  |  | 2
My Tasks | Able to view tasks in box |  | 0 |  | DO NOT ADD | 0 | 1
| Able to click on view all and be redirected to appropriate page |  |  |  | DO NOT ADD | 0 | 1
Total |  |  | 0 |  |  |  | 2
Recent Projects | Able to view recent projects in box |  | 0 |  | DO NOT ADD | 0 | 1
| Able to click on view all and be redirected to appropriate page |  |  |  | DO NOT ADD | 0 | 1
Total | [6 empty] | 2
Following | Able to view what you are following in box |  | 0 |  | DO NOT ADD | 0 | 1
| Able to click on view all and be redirected to appropriate page |  |  |  | DO NOT ADD | 0 | 1
Total | [6 empty] | 2
Onboarding | Able to view items in onboarding |  | 0 |  | DO NOT ADD | 0 | 1
| Create Profile | Clicking on these items should redirect you to the correct settings page to make these changes |  |  | DO NOT ADD | 0 | 1
| Manage your account |  |  |  | DO NOT ADD | 0 | 1
Total | [6 empty] | 3
Uber Total |  |  | 0 | #DIV/0! | 0 | <-Items added to portal
Grade |  |  | 0% | above is percent of functional beta feature on Portal. Over 100% marks merged features that are not functional (Will be highlighted in red), 100% mean all functional beta feature are merged into Portal (Will be marked in Green), less than 100% means not all functional beta features are merged into Portal (Will be blue).